Jatropha Seed Storage and Sowing Plan

Period: 15 Oct – 28 Dec 2026   /   Updated: 16 Oct 2026

# 1. Key points

- Total seed: 29,920 kg. Weekly sowing capacity is 3,080 kg (560 kg × 5 weekdays + 280 kg on Saturday), so this is about 9.7 weeks of work.

- Sowing period: Wed 21 Oct – Mon 28 Dec. The finish date is set by the arrival of Ghana 2 and Ghana 3, so starting on 21 Oct does not delay it.

- Peak storage: 18,720 kg (14–15 Nov). India (1,020 kg left) and Ghana 1 (3,000 kg) are still in stock when Ghana 3 (13 Nov) and Ghana 2 (14 Nov) arrive.

- Seed shortage: almost none. After sowing starts, the only shortfall is 60 kg on Sat 21 Nov (Ghana 1 runs out and Ghana 2 is ready from the next day). Sowing continues without a break from 21 Oct to 28 Dec.

- Reserve storage space for at least 19 tonnes, including the drying area.

# 2. Assumptions

- 100 workers sow 560 kg per day in total across all lots. Saturday is a half day (280 kg); Sunday is off.

- Lots are used in this order: Ribáuè 2026 → Ribáuè 2025 → Ghana 0 → India → Ghana 1 → Ghana 2 → Ghana 3. If a lot runs out partway through a day, the rest of that day's 560 kg comes from the next lot.

- Each new arrival dries for 7 days, counting the arrival day (drying continues on Sundays). Day 8 is for preparation and soaking, and sowing can start on day 9. None of the preparation days falls on a Sunday.

- First sowing day is Wed 21 Oct. The lots already in stock (Ribáuè 2026, Ribáuè 2025, Ghana 0) are already dry and are prepared and soaked on Tue 20 Oct.

- Preparation and soaking is lead time for each lot; other lots can still be sown on that day.

- Storage is the amount left in the warehouse (including the drying area) after each day's sowing. Public holidays are not included (see section 5).

# 3. Schedule by lot

| Lot | kg | Arrival | Drying | Prep & soak | Ready | Sowing | Days at 560 kg |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ribáuè 2026 | 1,326 | In stock | (already dry) | 20 Oct | 21 Oct | 21 Oct – 23 Oct | 2.4 |
| Ribáuè 2025 | 749 | In stock | (already dry) | 20 Oct | 21 Oct | 23 Oct – 26 Oct | 1.3 |
| Ghana 0 | 745 | In stock | (already dry) | 20 Oct | 21 Oct | 26 Oct – 27 Oct | 1.3 |
| India | 8,400 | 16 Oct | 16 Oct – 22 Oct | 23 Oct | 24 Oct | 27 Oct – 16 Nov | 15.0 |
| Ghana 1 | 3,000 | 21 Oct | 21 Oct – 27 Oct | 28 Oct | 29 Oct | 16 Nov – 21 Nov | 5.4 |
| Ghana 2 | 12,000 | 14 Nov | 14 Nov – 20 Nov | 21 Nov | 22 Nov | 23 Nov – 18 Dec | 21.4 |
| Ghana 3 | 3,700 | 13 Nov | 13 Nov – 19 Nov | 20 Nov | 21 Nov | 18 Dec – 28 Dec | 6.6 |

Note: India is ready from 24 Oct, Ghana 1 from 29 Oct and Ghana 3 from 21 Nov. To keep the set order, they are sown from 27 Oct, 16 Nov and 18 Dec.

# 4. Storage over time

Figure 1. Storage by lot after each day's sowing. The dotted line marks the first sowing day (21 Oct). Light red bands are working days without enough seed ready. Nothing is sown on Sundays, so storage stays the same as on Saturday.

## 4.1 Changes in storage

| Period | Storage (kg) | What happens |
| --- | --- | --- |
| 15 Oct | 2,820 | Only the lots already in stock: Ribáuè 2026, Ribáuè 2025, Ghana 0 |
| 16–20 Oct | 11,220 | India (8,400 kg) arrives and starts drying. No sowing yet; stock lots are prepared and soaked on 20 Oct |
| 21 Oct | 13,660 | Ghana 1 (3,000 kg) arrives. Sowing starts with Ribáuè 2026 |
| 22–26 Oct | 13,100 → 11,700 | Ribáuè 2026 (finished 23 Oct) and Ribáuè 2025 (finished 26 Oct) are sown; Ghana 0 starts |
| 27 Oct | 11,140 | Ghana 0 finished; India starts |
| 28 Oct – 12 Nov | 10,580 → 3,860 | India is sown |
| 13 Nov | 7,000 | Ghana 3 (3,700 kg) arrives |
| 14–15 Nov | 18,720 | Ghana 2 (12,000 kg) arrives (peak) |
| 16–21 Nov | 18,160 → 15,700 | India finished 16 Nov; Ghana 1 sown and finished 21 Nov |
| 22 Nov | 15,700 | Sunday |
| 23 Nov – 18 Dec | 15,140 → 3,660 | Ghana 2 is sown |
| 18–28 Dec | 3,660 → 0 | Ghana 3 is sown; sowing complete on 28 Dec |

## 4.2 Seed shortages

| Date | Sown (kg) | Short (kg) | Reason |
| --- | --- | --- | --- |
| Sat 21 Nov | 220 | 60 | Ghana 1 runs out; Ghana 2 is ready from 22 Nov (sown from 23 Nov) |
| Total |  | 60 | Almost no impact |

Note: 15–20 Oct is before sowing starts and is not counted as a shortage.

# 5. Notes and suggestions

- Finish date is 28 Dec: From 23 Nov, the 15,700 kg of Ghana 2 and Ghana 3 is sown without a break, so moving the start from 17 Oct to 21 Oct does not change the finish date. It also removes the idle working days of the earlier plan (23 Oct and 20–21 Nov).

- Higher peak: Because sowing starts later, India and Ghana 1 stay in stock until mid-November. The peak rises from 17,580 kg to 18,720 kg (+1,140 kg).

- Before sowing starts: 16–20 Oct can be used for preparation, such as digging planting holes, preparing fields and briefing workers.

- Holidays: 25 Dec (Family Day) is counted as a working day. If it is a day off, sowing finishes on Tue 29 Dec.

- Drying space: On 21–22 Oct, 11,400 kg (India and Ghana 1) is drying at the same time; on 14–19 Nov, 15,700 kg (Ghana 2 and Ghana 3). Size the drying area for these amounts.

- How much to soak: Soak only the next day's seed (560 kg on weekdays, 280 kg for Saturday) the day before. Because Sunday falls between Saturday and Monday, decide who soaks Monday's seed on Sunday, or soak it on Monday morning.

- Lots stored for a long time: India is kept for up to about 1 month after arrival (until 16 Nov), Ghana 1 for about 1 month (until 21 Nov) and Ghana 3 for about 1.5 months (until 28 Dec). Protect them from moisture and pests and inspect them regularly.

# Appendix: daily storage and sowing (kg)

Storage is after each day's sowing. Light red rows are days without enough seed; grey rows are Sundays (day off).

| Date | Rib 2026 | Rib 2025 | Ghana 0 | India | Ghana 1 | Ghana 2 | Ghana 3 | Total | Sown | Lots sown |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Thu 15 Oct | 1,326 | 749 | 745 | — | — | — | — | 2,820 | 0 | — |
| Fri 16 Oct | 1,326 | 749 | 745 | 8,400 | — | — | — | 11,220 | 0 | — |
| Sat 17 Oct | 1,326 | 749 | 745 | 8,400 | — | — | — | 11,220 | 0 | — |
| Sun 18 Oct | 1,326 | 749 | 745 | 8,400 | — | — | — | 11,220 | 0 | — |
| Mon 19 Oct | 1,326 | 749 | 745 | 8,400 | — | — | — | 11,220 | 0 | — |
| Tue 20 Oct | 1,326 | 749 | 745 | 8,400 | — | — | — | 11,220 | 0 | — |
| Wed 21 Oct | 766 | 749 | 745 | 8,400 | 3,000 | — | — | 13,660 | 560 | Ribáuè 2026 560 |
| Thu 22 Oct | 206 | 749 | 745 | 8,400 | 3,000 | — | — | 13,100 | 560 | Ribáuè 2026 560 |
| Fri 23 Oct | — | 395 | 745 | 8,400 | 3,000 | — | — | 12,540 | 560 | Ribáuè 2026 206 / Ribáuè 2025 354 |
| Sat 24 Oct | — | 115 | 745 | 8,400 | 3,000 | — | — | 12,260 | 280 | Ribáuè 2025 280 |
| Sun 25 Oct | — | 115 | 745 | 8,400 | 3,000 | — | — | 12,260 | 0 | — |
| Mon 26 Oct | — | — | 300 | 8,400 | 3,000 | — | — | 11,700 | 560 | Ribáuè 2025 115 / Ghana 0 445 |
| Tue 27 Oct | — | — | — | 8,140 | 3,000 | — | — | 11,140 | 560 | Ghana 0 300 / India 260 |
| Wed 28 Oct | — | — | — | 7,580 | 3,000 | — | — | 10,580 | 560 | India 560 |
| Thu 29 Oct | — | — | — | 7,020 | 3,000 | — | — | 10,020 | 560 | India 560 |
| Fri 30 Oct | — | — | — | 6,460 | 3,000 | — | — | 9,460 | 560 | India 560 |
| Sat 31 Oct | — | — | — | 6,180 | 3,000 | — | — | 9,180 | 280 | India 280 |
| Sun 1 Nov | — | — | — | 6,180 | 3,000 | — | — | 9,180 | 0 | — |
| Mon 2 Nov | — | — | — | 5,620 | 3,000 | — | — | 8,620 | 560 | India 560 |
| Tue 3 Nov | — | — | — | 5,060 | 3,000 | — | — | 8,060 | 560 | India 560 |
| Wed 4 Nov | — | — | — | 4,500 | 3,000 | — | — | 7,500 | 560 | India 560 |
| Thu 5 Nov | — | — | — | 3,940 | 3,000 | — | — | 6,940 | 560 | India 560 |
| Fri 6 Nov | — | — | — | 3,380 | 3,000 | — | — | 6,380 | 560 | India 560 |
| Sat 7 Nov | — | — | — | 3,100 | 3,000 | — | — | 6,100 | 280 | India 280 |
| Sun 8 Nov | — | — | — | 3,100 | 3,000 | — | — | 6,100 | 0 | — |
| Mon 9 Nov | — | — | — | 2,540 | 3,000 | — | — | 5,540 | 560 | India 560 |
| Tue 10 Nov | — | — | — | 1,980 | 3,000 | — | — | 4,980 | 560 | India 560 |
| Wed 11 Nov | — | — | — | 1,420 | 3,000 | — | — | 4,420 | 560 | India 560 |
| Thu 12 Nov | — | — | — | 860 | 3,000 | — | — | 3,860 | 560 | India 560 |
| Fri 13 Nov | — | — | — | 300 | 3,000 | — | 3,700 | 7,000 | 560 | India 560 |
| Sat 14 Nov | — | — | — | 20 | 3,000 | 12,000 | 3,700 | 18,720 | 280 | India 280 |
| Sun 15 Nov | — | — | — | 20 | 3,000 | 12,000 | 3,700 | 18,720 | 0 | — |
| Mon 16 Nov | — | — | — | — | 2,460 | 12,000 | 3,700 | 18,160 | 560 | India 20 / Ghana 1 540 |
| Tue 17 Nov | — | — | — | — | 1,900 | 12,000 | 3,700 | 17,600 | 560 | Ghana 1 560 |
| Wed 18 Nov | — | — | — | — | 1,340 | 12,000 | 3,700 | 17,040 | 560 | Ghana 1 560 |
| Thu 19 Nov | — | — | — | — | 780 | 12,000 | 3,700 | 16,480 | 560 | Ghana 1 560 |
| Fri 20 Nov | — | — | — | — | 220 | 12,000 | 3,700 | 15,920 | 560 | Ghana 1 560 |
| Sat 21 Nov | — | — | — | — | — | 12,000 | 3,700 | 15,700 | 220 | Ghana 1 220 |
| Sun 22 Nov | — | — | — | — | — | 12,000 | 3,700 | 15,700 | 0 | — |
| Mon 23 Nov | — | — | — | — | — | 11,440 | 3,700 | 15,140 | 560 | Ghana 2 560 |
| Tue 24 Nov | — | — | — | — | — | 10,880 | 3,700 | 14,580 | 560 | Ghana 2 560 |
| Wed 25 Nov | — | — | — | — | — | 10,320 | 3,700 | 14,020 | 560 | Ghana 2 560 |
| Thu 26 Nov | — | — | — | — | — | 9,760 | 3,700 | 13,460 | 560 | Ghana 2 560 |
| Fri 27 Nov | — | — | — | — | — | 9,200 | 3,700 | 12,900 | 560 | Ghana 2 560 |
| Sat 28 Nov | — | — | — | — | — | 8,920 | 3,700 | 12,620 | 280 | Ghana 2 280 |
| Sun 29 Nov | — | — | — | — | — | 8,920 | 3,700 | 12,620 | 0 | — |
| Mon 30 Nov | — | — | — | — | — | 8,360 | 3,700 | 12,060 | 560 | Ghana 2 560 |
| Tue 1 Dec | — | — | — | — | — | 7,800 | 3,700 | 11,500 | 560 | Ghana 2 560 |
| Wed 2 Dec | — | — | — | — | — | 7,240 | 3,700 | 10,940 | 560 | Ghana 2 560 |
| Thu 3 Dec | — | — | — | — | — | 6,680 | 3,700 | 10,380 | 560 | Ghana 2 560 |
| Fri 4 Dec | — | — | — | — | — | 6,120 | 3,700 | 9,820 | 560 | Ghana 2 560 |
| Sat 5 Dec | — | — | — | — | — | 5,840 | 3,700 | 9,540 | 280 | Ghana 2 280 |
| Sun 6 Dec | — | — | — | — | — | 5,840 | 3,700 | 9,540 | 0 | — |
| Mon 7 Dec | — | — | — | — | — | 5,280 | 3,700 | 8,980 | 560 | Ghana 2 560 |
| Tue 8 Dec | — | — | — | — | — | 4,720 | 3,700 | 8,420 | 560 | Ghana 2 560 |
| Wed 9 Dec | — | — | — | — | — | 4,160 | 3,700 | 7,860 | 560 | Ghana 2 560 |
| Thu 10 Dec | — | — | — | — | — | 3,600 | 3,700 | 7,300 | 560 | Ghana 2 560 |
| Fri 11 Dec | — | — | — | — | — | 3,040 | 3,700 | 6,740 | 560 | Ghana 2 560 |
| Sat 12 Dec | — | — | — | — | — | 2,760 | 3,700 | 6,460 | 280 | Ghana 2 280 |
| Sun 13 Dec | — | — | — | — | — | 2,760 | 3,700 | 6,460 | 0 | — |
| Mon 14 Dec | — | — | — | — | — | 2,200 | 3,700 | 5,900 | 560 | Ghana 2 560 |
| Tue 15 Dec | — | — | — | — | — | 1,640 | 3,700 | 5,340 | 560 | Ghana 2 560 |
| Wed 16 Dec | — | — | — | — | — | 1,080 | 3,700 | 4,780 | 560 | Ghana 2 560 |
| Thu 17 Dec | — | — | — | — | — | 520 | 3,700 | 4,220 | 560 | Ghana 2 560 |
| Fri 18 Dec | — | — | — | — | — | — | 3,660 | 3,660 | 560 | Ghana 2 520 / Ghana 3 40 |
| Sat 19 Dec | — | — | — | — | — | — | 3,380 | 3,380 | 280 | Ghana 3 280 |
| Sun 20 Dec | — | — | — | — | — | — | 3,380 | 3,380 | 0 | — |
| Mon 21 Dec | — | — | — | — | — | — | 2,820 | 2,820 | 560 | Ghana 3 560 |
| Tue 22 Dec | — | — | — | — | — | — | 2,260 | 2,260 | 560 | Ghana 3 560 |
| Wed 23 Dec | — | — | — | — | — | — | 1,700 | 1,700 | 560 | Ghana 3 560 |
| Thu 24 Dec | — | — | — | — | — | — | 1,140 | 1,140 | 560 | Ghana 3 560 |
| Fri 25 Dec | — | — | — | — | — | — | 580 | 580 | 560 | Ghana 3 560 |
| Sat 26 Dec | — | — | — | — | — | — | 300 | 300 | 280 | Ghana 3 280 |
| Sun 27 Dec | — | — | — | — | — | — | 300 | 300 | 0 | — |
| Mon 28 Dec | — | — | — | — | — | — | — | 0 | 300 | Ghana 3 300 |